## Lead
Insurance Management Application- ClaimSail
Group Number - 3
Team Lead & Frontend Lead- Sandesh A Ram
Backend Lead - Tushar Ranjan Nayak

## Status meeting
Status Meeting Group - 3
Meeting Date | Time | Progress Check | Meeting summary | Time | Problem Solving | Meeting summary | Time | Collaboration | Meeting summary
2020-08-07 | 13:30 | a | Discussed on the Schema structure | 17:00 | a | Finalised the schema structure | - | - | -
2020-08-08 | 10:30 | a | Set up Github and everyone updated to the same version of the tech stack | 13:30 | a | Started off with all entity creations | 17:30 | a | Status Update and Question Resolution meeting
2020-08-09 | 10:30 | a | Controller functionality Work Allocation | 14:00 | a | Authentication and Service Funcationalities allocation | 17:30 | a | Status Update and Question Resolution meeting
2020-08-10 | 10:30 | a | Service functionality Work allocation | 15:00 | a | Testing Backend with Postman | 17:30 | a | Status Update and Question Resolution meeting
2020-08-11 | 10:30 | a | Front-end component Allocation | 13:30 | a | UI design work Allocation | 17:30 | a | Status Update and Question Resolution meeting
2020-08-12 | 10:30 | a | Front end Functionality Allocation | 13:30 | a | Conflict resolution and workflow improvement meeting | 17:30 | a | Status Update and Question Resolution meeting
2020-08-13 | - | - | - | - | - | - | - | - | -
2020-08-14 | 10:30 | a | Integration and Checking for proper functioning and bugs | 12:30 | a | J-Unit Testing allocation | 17:30 | - | Status Update and Question Resolution meeting
2020-08-15 | 11:30 | a | PPT Discussion and creation | - | - | - | - | - | -
2020-08-16 | 11:30 | a | Demo Presentation | - | - | - | - | - | -

## Status Tracker
Project Status Check Report Team - 3
Sl no. | Employee ID | Name | Domain | Module | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-14
1 | 2563267 | Tushar | Database, Backend, Front end | User | ER Diagram | User entity creation | User controller + Authentication | User Services | Admin/customer functionalities in Question entity | Admin/customer functionalities in User entity | Testing
2 | 2563143 | MuthuPriya | Database, Backend, Front end | Question | E-R Diagram | Question entity creation | Question Controller functions | Question Service | About us component | Contact us component | Testing
3 | 2563147 | Nikita | Database, Backend, Front end | Policy Category | E-R Diagram | PolicyCategory entity | PolicyCategory Controller | PolicyCategory Services | Customer functionality -Display policycategory table | Customer functionality -Apply,display policy | Testing
4 | 2563594 | Sireesha | Database, Backend, Front end | Question | E-R Diagram | Question Repo | Question controller | Cusomerpolicy controller | Home Page & Registration Page | Login Page | Testing
5 | 2563265 | Navya | Database, Backend, Front end | User | E-R Diagram | Admin Controller | User Services - adding admin | User Services - View all customers, view by id | Customer Dashboard | Question table - View, Update | Testing
6 | 2563581 | Shalini | Database, Backend, Front end | Policy | E-R Diagram | Policy Entity Creation | Policy Controller | Policy Services | Customer Registration | Admin Dashboard | Testing
7 | 2563506 | Brindhaa | Database, Backend, Front end | CustomerPolicy | E-R Diagram | CustomerPolicy entity creation | Cusomerpolicy controller | CustomerPolicyService | Policy History Component | Adding Admin | Testing
8 | 2563963 | Sandesh | Database, Backend, Front end | User | E-R Diagram | User controller | Admin services for Update, delete customer | User Services for Update profile | Category table - CURD | Update Profile | Testing
9
10